## README
🌿 AKSHARVAN — SPRINT TRACKER
Prototype: Level 1 (Jadooi Jungle) · 8 Jun – 5 Jul 2025 · 42 Tasks · 432h Capacity
SHEET | CONTENTS | SPRINT
📋 All Tasks | Master backlog — every task in one view, grouped by sprint | All
🚀 Sprint 1 | Foundations + Art Direction · 9–14 Jun | Sprint 1
⚙️ Sprint 2 | Core Screens + Exercise Engine · 16–21 Jun | Sprint 2
🎙️ Sprint 3 | Voice + Cutscenes + Animation · 23–28 Jun | Sprint 3
✨ Sprint 4 | Polish + QA + Demo · 30 Jun–5 Jul | Sprint 4
👤 By Person | All tasks sorted by Nazish / Priyam / Aliya | All
TEAM · 6h/day · 6 days/sprint · 36h each per sprint · 432h total
👩‍💻 Nazish | Frontend · 36h/sprint | Login, World Map, Exercise Engine, Memory Game, Microinteractions, Responsive QA
👨‍💻 Priyam | Backend / Voice · 36h/sprint | React/PWA setup, Supabase, Howler.js, ASR voice, Progress sync, Performance
🎨 Aliya | Content / Design · 36h/sprint | Style bible, Tina/Toto puppets, Object illustrations, Cutscenes, Hindi narration scripts, Audio gen
COLOUR KEY
🩷 Pink left border
🩵 Blue left border
💛 Gold left border
P1 (red) | Critical priority
P2 (orange) | High priority
P3 (yellow) | Medium priority
P4 (green) | Low priority
Purple Hrs Est cell | Planned hours — do not edit
Green Hrs Actual cell | Fill in as you go ✏️

## 📋 All Tasks
🌿 AKSHARVAN — MASTER TASK TRACKER ¦ 42 Tasks · 432h Capacity ¦ 8 Jun – 5 Jul 2025
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
Sprint 1 · 9–14 Jun · 64h estimated
A-01 | 1 | Priyam | Epic A — Foundations | Initialize React+TS+Vite project | 4 |  | P1 | 09/06 | 09/06 | Set up repo, Vite config, TypeScript strict mode, ESLint/Prettier.
A-02 | 2 | Nazish | Epic A — Foundations | Configure Tailwind CSS + Framer Motion | 3 |  | P1 | 09/06 | 09/06 | Mobile-first breakpoints. Base theme tokens.
A-03 | 3 | Priyam | Epic A — Foundations | PWA shell + service worker caching | 5 |  | P1 | 10/06 | 10/06 | vite-plugin-pwa, manifest.json, offline asset caching.
A-04 | 4 | Priyam | Epic A — Foundations | Supabase: auth + tables + storage | 6 |  | P1 | 10/06 | 11/06 | Tables: profiles, progress. Storage for assets+audio. RLS policies.
A-05 | 5 | Nazish | Epic A — Foundations | Define content JSON schema | 3 |  | P1 | 10/06 | 10/06 | TypeScript interfaces. Stub Level 1 JSON with all 6 pairs.
A-06 | 6 | Priyam | Epic A — Foundations | Deploy pipeline: Vercel + CI on push | 4 |  | P2 | 11/06 | 11/06 | Connect GitHub to Vercel. Env vars for Supabase.
A-07 | 7 | Nazish | Epic A — Foundations | React Router + screen scaffolding | 3 |  | P2 | 11/06 | 11/06 | Empty shell components for all 7 screens.
F-01 | 8 | Aliya | Epic F — Art Assets | Style bible: palette, line style, typography | 8 |  | P1 | 09/06 | 11/06 | Must be signed off before illustrations begin.
F-02 | 9 | Aliya | Epic F — Art Assets | Tina & Toto SVG puppets (3 age variants each) | 10 |  | P1 | 11/06 | 13/06 | Layered SVGs for Lottie animation.
F-03 | 10 | Aliya | Epic F — Art Assets | Object illustrations ×10 | 10 |  | P1 | 12/06 | 14/06 | बतख सपेरा पतंग रस्सी अनार घड़ी तरबूज कछुआ चम्मच लट्टू
F-04 | 11 | Aliya | Epic F — Art Assets | Letter tile designs ×10 | 4 |  | P2 | 13/06 | 13/06 | ब स प र अ घ त क च ल
D-01 | 12 | Aliya | Epic D — Voice | Write all Hindi narration scripts (ALfA-correct) | 4 |  | P1 | 12/06 | 13/06 | ALfA rule: 'बतख — ब', NOT 'ब से बतख'. ~80 lines.
Sprint 2 · 16–21 Jun · 73h estimated
B-01 | 13 | Nazish | Epic B — Core Screens | Login / profile screen | 5 |  | P1 | 16/06 | 16/06 | Phone input, language locked, age slider 4–10.
B-02 | 14 | Nazish | Epic B — Core Screens | Main menu screen (puppets + Play/Settings) | 4 |  | P1 | 17/06 | 17/06 | Idle animation via Framer Motion.
B-03 | 15 | Nazish | Epic B — Core Screens | World map (Level 1 active, others locked) | 5 |  | P1 | 17/06 | 18/06 | Do NOT hard-code linear unlock.
B-04 | 16 | Nazish | Epic B — Core Screens | Settings screen | 3 |  | P3 | 18/06 | 18/06 | Age/avatar, mute, language, logout.
B-05 | 17 | Nazish | Epic B — Core Screens | Level Complete screen | 3 |  | P2 | 18/06 | 18/06 | Restoration animation + celebration.
C-01 | 18 | Nazish | Epic C — Exercise Engine | Generic exercise engine (E1–E5) | 8 |  | P1 | 19/06 | 20/06 | Reads content JSON — no hardcoding.
C-02 | 19 | Nazish | Epic C — Exercise Engine | Matching / word-build component (E6) | 4 |  | P1 | 20/06 | 20/06 | Drag tiles; pass = 3 words built.
C-03 | 20 | Nazish | Epic C — Exercise Engine | Memory game component (E7) | 4 |  | P1 | 21/06 | 21/06 | 4×2 grid; reveal 2.5s; flip-back 1.5s.
C-04 | 21 | Nazish | Epic C — Exercise Engine | Forest restoration state controller | 4 |  | P2 | 21/06 | 21/06 | 7 layered states, decolorized → full.
P-01 | 22 | Priyam | Epic A — Foundations | Progress persistence: save/load Supabase | 5 |  | P1 | 16/06 | 17/06 | Offline queue + sync on reconnect.
P-02 | 23 | Priyam | Epic A — Foundations | Auth flow: phone → OTP → profile create | 4 |  | P1 | 16/06 | 16/06 | Token refresh handled silently.
F-05 | 24 | Aliya | Epic F — Art Assets | Jadooi Jungle background: all 7 layered states | 8 |  | P1 | 16/06 | 19/06 | ONE scene, toggleable layers — no re-generation.
F-06 | 25 | Aliya | Epic F — Art Assets | Backgrounds: Main Menu + World Map | 5 |  | P2 | 19/06 | 20/06 | WebP, mobile portrait dimensions.
D-02 | 26 | Aliya | Epic D — Voice | Generate + compress all TTS audio clips | 6 |  | P1 | 16/06 | 18/06 | Sarvam AI / ElevenLabs · 24–32 kbps Opus · ~80 files.
D-03 | 27 | Priyam | Epic D — Voice | Howler.js audio layer + autoplay unlock | 5 |  | P1 | 19/06 | 20/06 | First-tap gesture unlock on mobile.
Sprint 3 · 23–28 Jun · 72h estimated
D-04 | 28 | Priyam | Epic D — Voice | ASR: Web Speech API + closed-vocab matching | 8 |  | P1 | 23/06 | 24/06 | 6s timeout; no open transcription.
D-05 | 29 | Nazish | Epic D — Voice | Tap fallback: always-visible options | 4 |  | P1 | 23/06 | 23/06 | Both paths → same success/retry logic.
D-06 | 30 | Priyam | Epic D — Voice | Wire TTS audio to exercise engine timing | 4 |  | P1 | 24/06 | 24/06 | Narration end → mic open → auto-advance.
D-07 | 31 | Priyam | Epic D — Voice | Consented answer-clip recording | 5 |  | P3 | 25/06 | 25/06 | Only if consent flag set on profile.
E-01 | 32 | Aliya | Epic E — Cutscenes & Anim | World intro cutscene (Lottie/MP4) | 8 |  | P1 | 23/06 | 25/06 | ~30s · skippable · <2 MB.
E-02 | 33 | Aliya | Epic E — Cutscenes & Anim | Jadooi Jungle backstory cutscene | 6 |  | P2 | 25/06 | 26/06 | ~20s · skippable · <1.5 MB.
E-03 | 34 | Aliya | Epic E — Cutscenes & Anim | Lottie: puppet idles, celebration, tile flip | 8 |  | P1 | 24/06 | 26/06 | 5 files · <100 KB each · loop-safe.
E-04 | 35 | Nazish | Epic E — Cutscenes & Anim | Integrate cutscenes into app flow | 5 |  | P1 | 25/06 | 26/06 | Lazy-load; lottie-react.
E-05 | 36 | Nazish | Epic E — Cutscenes & Anim | Microinteraction pass (Framer Motion) | 6 |  | P2 | 26/06 | 27/06 | Disable on prefers-reduced-motion.
F-07 | 37 | Aliya | Epic F — Art Assets | Backgrounds: World Intro + Backstory scenes | 6 |  | P2 | 23/06 | 24/06 | Consistent with style bible.
F-08 | 38 | Aliya | Epic F — Art Assets | Asset export optimization (WebP/AVIF/SVG) | 4 |  | P2 | 27/06 | 27/06 | Object <25 KB · BG <80 KB · tile <5 KB.
C-05 | 39 | Nazish | Epic C — Exercise Engine | Level 1 content JSON: wire all 6 sub-levels | 5 |  | P1 | 23/06 | 24/06 | All 6 pairs with real audio paths wired.
C-06 | 40 | Priyam | Epic C — Exercise Engine | Restoration events: sub-level → forest layer | 3 |  | P2 | 26/06 | 26/06 | 1→sky 2→grass 3→trees 4→river 5→animals 6→full
Sprint 4 · 30 Jun–5 Jul · 60h estimated
G-01 | 41 | Nazish | Epic G — Polish & QA | End-to-end flow QA (all 6 sub-levels) | 6 |  | P1 | 30/06 | 01/07 | Full play-through; fix stuck states.
G-02 | 42 | Priyam | Epic G — Polish & QA | Low-end device + weak network testing | 4 |  | P1 | 30/06 | 30/06 | Moto E tier · 3G throttle.
G-03 | 43 | Aliya | Epic G — Polish & QA | Pedagogy QA: narration audit vs ALfA | 4 |  | P1 | 30/06 | 01/07 | Flag any 'ब से बतख' violations.
G-04 | 44 | Nazish | Epic G — Polish & QA | Responsive QA: 360px + 1280px | 5 |  | P2 | 01/07 | 01/07 | All touch targets ≥44×44 px.
G-05 | 45 | Nazish | Epic G — Polish & QA | Microinteraction final polish | 4 |  | P3 | 02/07 | 02/07 | Remove distracting animations.
G-06 | 46 | Priyam | Epic G — Polish & QA | Performance: bundle size + Lighthouse | 5 |  | P1 | 01/07 | 02/07 | Target FCP <2s on 3G · PWA score >90.
G-07 | 47 | Priyam | Epic G — Polish & QA | Audio QA: all clips in flow | 4 |  | P2 | 02/07 | 02/07 | No double-plays · test mute toggle.
G-08 | 48 | Aliya | Epic G — Polish & QA | Final asset QA + missing delivery | 6 |  | P1 | 01/07 | 02/07 | Audit all content JSON asset refs.
G-09 | 49 | Nazish | Epic G — Polish & QA | Accessibility: contrast, targets, motion | 4 |  | P2 | 03/07 | 03/07 | WCAG AA · prefers-reduced-motion.
G-10 | 50 | Priyam | Epic G — Polish & QA | Privacy & data audit (DPDP Act basics) | 3 |  | P2 | 03/07 | 03/07 | No 3rd-party trackers · RLS reviewed.
G-11 | 51 | Team | Epic G — Polish & QA | Demo build: share link + walkthrough doc | 5 |  | P1 | 04/07 | 04/07 | Vercel prod URL + 1-page walkthrough.
G-12 | 52 | Aliya | Epic G — Polish & QA | Demo prep: flow script + talking points | 3 |  | P2 | 03/07 | 04/07 | 10-min demo script for stakeholders.
G-13 | 53 | Priyam | Epic G — Polish & QA | Sprint retro + Level 2 backlog | 4 |  | P3 | 04/07 | 04/07 | Document Flutter migration path.
G-14 | 54 | Nazish | Epic G — Polish & QA | Fix P0/P1 bugs from QA sweep | 3 |  | P1 | 03/07 | 04/07 | Regression test after each fix.
TOTALS

## 🚀 Sprint 1
🚀 Sprint 1 · 9–14 Jun 2025 · 64h Estimated
🎯 Sprint Goal: Dev env live · JSON schema defined · backend scaffolded · style bible done · Tina/Toto puppets drafted · illustrations started.
Nazish 👩‍💻: 9h / 36h ¦ Priyam 👨‍💻: 19h / 36h ¦ Aliya 🎨: 36h / 36h
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
▸ Epic A — Foundations
A-01 | 1 | Priyam | Epic A — Foundations | Initialize React+TS+Vite project | 4 |  | P1 | 09/06 | 09/06 | Set up repo, Vite config, TypeScript strict mode, ESLint/Prettier.
A-02 | 2 | Nazish | Epic A — Foundations | Configure Tailwind CSS + Framer Motion | 3 |  | P1 | 09/06 | 09/06 | Mobile-first breakpoints. Base theme tokens.
A-03 | 3 | Priyam | Epic A — Foundations | PWA shell + service worker caching | 5 |  | P1 | 10/06 | 10/06 | vite-plugin-pwa, manifest.json, offline asset caching.
A-04 | 4 | Priyam | Epic A — Foundations | Supabase: auth + tables + storage | 6 |  | P1 | 10/06 | 11/06 | Tables: profiles, progress. Storage for assets+audio. RLS policies.
A-05 | 5 | Nazish | Epic A — Foundations | Define content JSON schema | 3 |  | P1 | 10/06 | 10/06 | TypeScript interfaces. Stub Level 1 JSON with all 6 pairs.
A-06 | 6 | Priyam | Epic A — Foundations | Deploy pipeline: Vercel + CI on push | 4 |  | P2 | 11/06 | 11/06 | Connect GitHub to Vercel. Env vars for Supabase.
A-07 | 7 | Nazish | Epic A — Foundations | React Router + screen scaffolding | 3 |  | P2 | 11/06 | 11/06 | Empty shell components for all 7 screens.
▸ Epic F — Art Assets
F-01 | 8 | Aliya | Epic F — Art Assets | Style bible: palette, line style, typography | 8 |  | P1 | 09/06 | 11/06 | Must be signed off before illustrations begin.
F-02 | 9 | Aliya | Epic F — Art Assets | Tina & Toto SVG puppets (3 age variants each) | 10 |  | P1 | 11/06 | 13/06 | Layered SVGs for Lottie animation.
F-03 | 10 | Aliya | Epic F — Art Assets | Object illustrations ×10 | 10 |  | P1 | 12/06 | 14/06 | बतख सपेरा पतंग रस्सी अनार घड़ी तरबूज कछुआ चम्मच लट्टू
F-04 | 11 | Aliya | Epic F — Art Assets | Letter tile designs ×10 | 4 |  | P2 | 13/06 | 13/06 | ब स प र अ घ त क च ल
▸ Epic D — Voice
D-01 | 12 | Aliya | Epic D — Voice | Write all Hindi narration scripts (ALfA-correct) | 4 |  | P1 | 12/06 | 13/06 | ALfA rule: 'बतख — ब', NOT 'ब से बतख'. ~80 lines.
TOTALS

## ⚙️ Sprint 2
⚙️ Sprint 2 · 16–21 Jun 2025 · 73h Estimated
🎯 Sprint Goal: Login · Menu · Map · Settings · Level Complete built · exercise engine E1–E7 working · forest restoration controller wired.
Nazish 👩‍💻: 40h / 36h ¦ Priyam 👨‍💻: 14h / 36h ¦ Aliya 🎨: 19h / 36h
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
▸ Epic B — Core Screens
B-01 | 1 | Nazish | Epic B — Core Screens | Login / profile screen | 5 |  | P1 | 16/06 | 16/06 | Phone input, language locked, age slider 4–10.
B-02 | 2 | Nazish | Epic B — Core Screens | Main menu screen (puppets + Play/Settings) | 4 |  | P1 | 17/06 | 17/06 | Idle animation via Framer Motion.
B-03 | 3 | Nazish | Epic B — Core Screens | World map (Level 1 active, others locked) | 5 |  | P1 | 17/06 | 18/06 | Do NOT hard-code linear unlock.
B-04 | 4 | Nazish | Epic B — Core Screens | Settings screen | 3 |  | P3 | 18/06 | 18/06 | Age/avatar, mute, language, logout.
B-05 | 5 | Nazish | Epic B — Core Screens | Level Complete screen | 3 |  | P2 | 18/06 | 18/06 | Restoration animation + celebration.
▸ Epic C — Exercise Engine
C-01 | 6 | Nazish | Epic C — Exercise Engine | Generic exercise engine (E1–E5) | 8 |  | P1 | 19/06 | 20/06 | Reads content JSON — no hardcoding.
C-02 | 7 | Nazish | Epic C — Exercise Engine | Matching / word-build component (E6) | 4 |  | P1 | 20/06 | 20/06 | Drag tiles; pass = 3 words built.
C-03 | 8 | Nazish | Epic C — Exercise Engine | Memory game component (E7) | 4 |  | P1 | 21/06 | 21/06 | 4×2 grid; reveal 2.5s; flip-back 1.5s.
C-04 | 9 | Nazish | Epic C — Exercise Engine | Forest restoration state controller | 4 |  | P2 | 21/06 | 21/06 | 7 layered states, decolorized → full.
▸ Epic A — Foundations
P-01 | 10 | Priyam | Epic A — Foundations | Progress persistence: save/load Supabase | 5 |  | P1 | 16/06 | 17/06 | Offline queue + sync on reconnect.
P-02 | 11 | Priyam | Epic A — Foundations | Auth flow: phone → OTP → profile create | 4 |  | P1 | 16/06 | 16/06 | Token refresh handled silently.
▸ Epic F — Art Assets
F-05 | 12 | Aliya | Epic F — Art Assets | Jadooi Jungle background: all 7 layered states | 8 |  | P1 | 16/06 | 19/06 | ONE scene, toggleable layers — no re-generation.
F-06 | 13 | Aliya | Epic F — Art Assets | Backgrounds: Main Menu + World Map | 5 |  | P2 | 19/06 | 20/06 | WebP, mobile portrait dimensions.
▸ Epic D — Voice
D-02 | 14 | Aliya | Epic D — Voice | Generate + compress all TTS audio clips | 6 |  | P1 | 16/06 | 18/06 | Sarvam AI / ElevenLabs · 24–32 kbps Opus · ~80 files.
D-03 | 15 | Priyam | Epic D — Voice | Howler.js audio layer + autoplay unlock | 5 |  | P1 | 19/06 | 20/06 | First-tap gesture unlock on mobile.
TOTALS

## 🎙️ Sprint 3
🎙️ Sprint 3 · 23–28 Jun 2025 · 72h Estimated
🎯 Sprint Goal: TTS clips integrated · ASR live with tap fallback · cutscenes integrated · Lottie animations done · real content wired.
Nazish 👩‍💻: 20h / 36h ¦ Priyam 👨‍💻: 20h / 36h ¦ Aliya 🎨: 32h / 36h
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
▸ Epic D — Voice
D-04 | 1 | Priyam | Epic D — Voice | ASR: Web Speech API + closed-vocab matching | 8 |  | P1 | 23/06 | 24/06 | 6s timeout; no open transcription.
D-05 | 2 | Nazish | Epic D — Voice | Tap fallback: always-visible options | 4 |  | P1 | 23/06 | 23/06 | Both paths → same success/retry logic.
D-06 | 3 | Priyam | Epic D — Voice | Wire TTS audio to exercise engine timing | 4 |  | P1 | 24/06 | 24/06 | Narration end → mic open → auto-advance.
D-07 | 4 | Priyam | Epic D — Voice | Consented answer-clip recording | 5 |  | P3 | 25/06 | 25/06 | Only if consent flag set on profile.
▸ Epic E — Cutscenes & Anim
E-01 | 5 | Aliya | Epic E — Cutscenes & Anim | World intro cutscene (Lottie/MP4) | 8 |  | P1 | 23/06 | 25/06 | ~30s · skippable · <2 MB.
E-02 | 6 | Aliya | Epic E — Cutscenes & Anim | Jadooi Jungle backstory cutscene | 6 |  | P2 | 25/06 | 26/06 | ~20s · skippable · <1.5 MB.
E-03 | 7 | Aliya | Epic E — Cutscenes & Anim | Lottie: puppet idles, celebration, tile flip | 8 |  | P1 | 24/06 | 26/06 | 5 files · <100 KB each · loop-safe.
E-04 | 8 | Nazish | Epic E — Cutscenes & Anim | Integrate cutscenes into app flow | 5 |  | P1 | 25/06 | 26/06 | Lazy-load; lottie-react.
E-05 | 9 | Nazish | Epic E — Cutscenes & Anim | Microinteraction pass (Framer Motion) | 6 |  | P2 | 26/06 | 27/06 | Disable on prefers-reduced-motion.
▸ Epic F — Art Assets
F-07 | 10 | Aliya | Epic F — Art Assets | Backgrounds: World Intro + Backstory scenes | 6 |  | P2 | 23/06 | 24/06 | Consistent with style bible.
F-08 | 11 | Aliya | Epic F — Art Assets | Asset export optimization (WebP/AVIF/SVG) | 4 |  | P2 | 27/06 | 27/06 | Object <25 KB · BG <80 KB · tile <5 KB.
▸ Epic C — Exercise Engine
C-05 | 12 | Nazish | Epic C — Exercise Engine | Level 1 content JSON: wire all 6 sub-levels | 5 |  | P1 | 23/06 | 24/06 | All 6 pairs with real audio paths wired.
C-06 | 13 | Priyam | Epic C — Exercise Engine | Restoration events: sub-level → forest layer | 3 |  | P2 | 26/06 | 26/06 | 1→sky 2→grass 3→trees 4→river 5→animals 6→full
TOTALS

## ✨ Sprint 4
✨ Sprint 4 · 30 Jun–5 Jul 2025 · 60h Estimated
🎯 Sprint Goal: End-to-end QA passed · low-end device tested · pedagogy audit done · microinteractions complete · demo build live on Vercel.
Nazish 👩‍💻: 22h / 36h ¦ Priyam 👨‍💻: 20h / 36h ¦ Aliya 🎨: 13h / 36h
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
▸ Epic G — Polish & QA
G-01 | 1 | Nazish | Epic G — Polish & QA | End-to-end flow QA (all 6 sub-levels) | 6 |  | P1 | 30/06 | 01/07 | Full play-through; fix stuck states.
G-02 | 2 | Priyam | Epic G — Polish & QA | Low-end device + weak network testing | 4 |  | P1 | 30/06 | 30/06 | Moto E tier · 3G throttle.
G-03 | 3 | Aliya | Epic G — Polish & QA | Pedagogy QA: narration audit vs ALfA | 4 |  | P1 | 30/06 | 01/07 | Flag any 'ब से बतख' violations.
G-04 | 4 | Nazish | Epic G — Polish & QA | Responsive QA: 360px + 1280px | 5 |  | P2 | 01/07 | 01/07 | All touch targets ≥44×44 px.
G-05 | 5 | Nazish | Epic G — Polish & QA | Microinteraction final polish | 4 |  | P3 | 02/07 | 02/07 | Remove distracting animations.
G-06 | 6 | Priyam | Epic G — Polish & QA | Performance: bundle size + Lighthouse | 5 |  | P1 | 01/07 | 02/07 | Target FCP <2s on 3G · PWA score >90.
G-07 | 7 | Priyam | Epic G — Polish & QA | Audio QA: all clips in flow | 4 |  | P2 | 02/07 | 02/07 | No double-plays · test mute toggle.
G-08 | 8 | Aliya | Epic G — Polish & QA | Final asset QA + missing delivery | 6 |  | P1 | 01/07 | 02/07 | Audit all content JSON asset refs.
G-09 | 9 | Nazish | Epic G — Polish & QA | Accessibility: contrast, targets, motion | 4 |  | P2 | 03/07 | 03/07 | WCAG AA · prefers-reduced-motion.
G-10 | 10 | Priyam | Epic G — Polish & QA | Privacy & data audit (DPDP Act basics) | 3 |  | P2 | 03/07 | 03/07 | No 3rd-party trackers · RLS reviewed.
G-11 | 11 | Team | Epic G — Polish & QA | Demo build: share link + walkthrough doc | 5 |  | P1 | 04/07 | 04/07 | Vercel prod URL + 1-page walkthrough.
G-12 | 12 | Aliya | Epic G — Polish & QA | Demo prep: flow script + talking points | 3 |  | P2 | 03/07 | 04/07 | 10-min demo script for stakeholders.
G-13 | 13 | Priyam | Epic G — Polish & QA | Sprint retro + Level 2 backlog | 4 |  | P3 | 04/07 | 04/07 | Document Flutter migration path.
G-14 | 14 | Nazish | Epic G — Polish & QA | Fix P0/P1 bugs from QA sweep | 3 |  | P1 | 03/07 | 04/07 | Regression test after each fix.
TOTALS

## 👤 By Person
👤 TASKS BY PERSON · Aksharvan Sprint Plan
ID | # | Owner | Epic | Task / Story | Hrs Est. | Hrs Actual | Priority | Start | End | Notes / AC | Done?
👩‍💻 Nazish · Frontend · 91h across 4 sprints
A-02 | 1 | Nazish | Epic A — Foundations | Configure Tailwind CSS + Framer Motion | 3 |  | P1 | 09/06 | 09/06 | Mobile-first breakpoints. Base theme tokens.
A-05 | 2 | Nazish | Epic A — Foundations | Define content JSON schema | 3 |  | P1 | 10/06 | 10/06 | TypeScript interfaces. Stub Level 1 JSON with all 6 pairs.
A-07 | 3 | Nazish | Epic A — Foundations | React Router + screen scaffolding | 3 |  | P2 | 11/06 | 11/06 | Empty shell components for all 7 screens.
B-01 | 4 | Nazish | Epic B — Core Screens | Login / profile screen | 5 |  | P1 | 16/06 | 16/06 | Phone input, language locked, age slider 4–10.
B-02 | 5 | Nazish | Epic B — Core Screens | Main menu screen (puppets + Play/Settings) | 4 |  | P1 | 17/06 | 17/06 | Idle animation via Framer Motion.
B-03 | 6 | Nazish | Epic B — Core Screens | World map (Level 1 active, others locked) | 5 |  | P1 | 17/06 | 18/06 | Do NOT hard-code linear unlock.
B-04 | 7 | Nazish | Epic B — Core Screens | Settings screen | 3 |  | P3 | 18/06 | 18/06 | Age/avatar, mute, language, logout.
B-05 | 8 | Nazish | Epic B — Core Screens | Level Complete screen | 3 |  | P2 | 18/06 | 18/06 | Restoration animation + celebration.
C-01 | 9 | Nazish | Epic C — Exercise Engine | Generic exercise engine (E1–E5) | 8 |  | P1 | 19/06 | 20/06 | Reads content JSON — no hardcoding.
C-02 | 10 | Nazish | Epic C — Exercise Engine | Matching / word-build component (E6) | 4 |  | P1 | 20/06 | 20/06 | Drag tiles; pass = 3 words built.
C-03 | 11 | Nazish | Epic C — Exercise Engine | Memory game component (E7) | 4 |  | P1 | 21/06 | 21/06 | 4×2 grid; reveal 2.5s; flip-back 1.5s.
C-04 | 12 | Nazish | Epic C — Exercise Engine | Forest restoration state controller | 4 |  | P2 | 21/06 | 21/06 | 7 layered states, decolorized → full.
D-05 | 13 | Nazish | Epic D — Voice | Tap fallback: always-visible options | 4 |  | P1 | 23/06 | 23/06 | Both paths → same success/retry logic.
E-04 | 14 | Nazish | Epic E — Cutscenes & Anim | Integrate cutscenes into app flow | 5 |  | P1 | 25/06 | 26/06 | Lazy-load; lottie-react.
E-05 | 15 | Nazish | Epic E — Cutscenes & Anim | Microinteraction pass (Framer Motion) | 6 |  | P2 | 26/06 | 27/06 | Disable on prefers-reduced-motion.
C-05 | 16 | Nazish | Epic C — Exercise Engine | Level 1 content JSON: wire all 6 sub-levels | 5 |  | P1 | 23/06 | 24/06 | All 6 pairs with real audio paths wired.
G-01 | 17 | Nazish | Epic G — Polish & QA | End-to-end flow QA (all 6 sub-levels) | 6 |  | P1 | 30/06 | 01/07 | Full play-through; fix stuck states.
G-04 | 18 | Nazish | Epic G — Polish & QA | Responsive QA: 360px + 1280px | 5 |  | P2 | 01/07 | 01/07 | All touch targets ≥44×44 px.
G-05 | 19 | Nazish | Epic G — Polish & QA | Microinteraction final polish | 4 |  | P3 | 02/07 | 02/07 | Remove distracting animations.
G-09 | 20 | Nazish | Epic G — Polish & QA | Accessibility: contrast, targets, motion | 4 |  | P2 | 03/07 | 03/07 | WCAG AA · prefers-reduced-motion.
G-14 | 21 | Nazish | Epic G — Polish & QA | Fix P0/P1 bugs from QA sweep | 3 |  | P1 | 03/07 | 04/07 | Regression test after each fix.
Nazish Subtotal
👨‍💻 Priyam · Backend / Voice · 73h across 4 sprints
A-01 | 1 | Priyam | Epic A — Foundations | Initialize React+TS+Vite project | 4 |  | P1 | 09/06 | 09/06 | Set up repo, Vite config, TypeScript strict mode, ESLint/Prettier.
A-03 | 2 | Priyam | Epic A — Foundations | PWA shell + service worker caching | 5 |  | P1 | 10/06 | 10/06 | vite-plugin-pwa, manifest.json, offline asset caching.
A-04 | 3 | Priyam | Epic A — Foundations | Supabase: auth + tables + storage | 6 |  | P1 | 10/06 | 11/06 | Tables: profiles, progress. Storage for assets+audio. RLS policies.
A-06 | 4 | Priyam | Epic A — Foundations | Deploy pipeline: Vercel + CI on push | 4 |  | P2 | 11/06 | 11/06 | Connect GitHub to Vercel. Env vars for Supabase.
P-01 | 5 | Priyam | Epic A — Foundations | Progress persistence: save/load Supabase | 5 |  | P1 | 16/06 | 17/06 | Offline queue + sync on reconnect.
P-02 | 6 | Priyam | Epic A — Foundations | Auth flow: phone → OTP → profile create | 4 |  | P1 | 16/06 | 16/06 | Token refresh handled silently.
D-03 | 7 | Priyam | Epic D — Voice | Howler.js audio layer + autoplay unlock | 5 |  | P1 | 19/06 | 20/06 | First-tap gesture unlock on mobile.
D-04 | 8 | Priyam | Epic D — Voice | ASR: Web Speech API + closed-vocab matching | 8 |  | P1 | 23/06 | 24/06 | 6s timeout; no open transcription.
D-06 | 9 | Priyam | Epic D — Voice | Wire TTS audio to exercise engine timing | 4 |  | P1 | 24/06 | 24/06 | Narration end → mic open → auto-advance.
D-07 | 10 | Priyam | Epic D — Voice | Consented answer-clip recording | 5 |  | P3 | 25/06 | 25/06 | Only if consent flag set on profile.
C-06 | 11 | Priyam | Epic C — Exercise Engine | Restoration events: sub-level → forest layer | 3 |  | P2 | 26/06 | 26/06 | 1→sky 2→grass 3→trees 4→river 5→animals 6→full
G-02 | 12 | Priyam | Epic G — Polish & QA | Low-end device + weak network testing | 4 |  | P1 | 30/06 | 30/06 | Moto E tier · 3G throttle.
G-06 | 13 | Priyam | Epic G — Polish & QA | Performance: bundle size + Lighthouse | 5 |  | P1 | 01/07 | 02/07 | Target FCP <2s on 3G · PWA score >90.
G-07 | 14 | Priyam | Epic G — Polish & QA | Audio QA: all clips in flow | 4 |  | P2 | 02/07 | 02/07 | No double-plays · test mute toggle.
G-10 | 15 | Priyam | Epic G — Polish & QA | Privacy & data audit (DPDP Act basics) | 3 |  | P2 | 03/07 | 03/07 | No 3rd-party trackers · RLS reviewed.
G-13 | 16 | Priyam | Epic G — Polish & QA | Sprint retro + Level 2 backlog | 4 |  | P3 | 04/07 | 04/07 | Document Flutter migration path.
Priyam Subtotal
🎨 Aliya · Content / Design · 100h across 4 sprints
F-01 | 1 | Aliya | Epic F — Art Assets | Style bible: palette, line style, typography | 8 |  | P1 | 09/06 | 11/06 | Must be signed off before illustrations begin.
F-02 | 2 | Aliya | Epic F — Art Assets | Tina & Toto SVG puppets (3 age variants each) | 10 |  | P1 | 11/06 | 13/06 | Layered SVGs for Lottie animation.
F-03 | 3 | Aliya | Epic F — Art Assets | Object illustrations ×10 | 10 |  | P1 | 12/06 | 14/06 | बतख सपेरा पतंग रस्सी अनार घड़ी तरबूज कछुआ चम्मच लट्टू
F-04 | 4 | Aliya | Epic F — Art Assets | Letter tile designs ×10 | 4 |  | P2 | 13/06 | 13/06 | ब स प र अ घ त क च ल
D-01 | 5 | Aliya | Epic D — Voice | Write all Hindi narration scripts (ALfA-correct) | 4 |  | P1 | 12/06 | 13/06 | ALfA rule: 'बतख — ब', NOT 'ब से बतख'. ~80 lines.
F-05 | 6 | Aliya | Epic F — Art Assets | Jadooi Jungle background: all 7 layered states | 8 |  | P1 | 16/06 | 19/06 | ONE scene, toggleable layers — no re-generation.
F-06 | 7 | Aliya | Epic F — Art Assets | Backgrounds: Main Menu + World Map | 5 |  | P2 | 19/06 | 20/06 | WebP, mobile portrait dimensions.
D-02 | 8 | Aliya | Epic D — Voice | Generate + compress all TTS audio clips | 6 |  | P1 | 16/06 | 18/06 | Sarvam AI / ElevenLabs · 24–32 kbps Opus · ~80 files.
E-01 | 9 | Aliya | Epic E — Cutscenes & Anim | World intro cutscene (Lottie/MP4) | 8 |  | P1 | 23/06 | 25/06 | ~30s · skippable · <2 MB.
E-02 | 10 | Aliya | Epic E — Cutscenes & Anim | Jadooi Jungle backstory cutscene | 6 |  | P2 | 25/06 | 26/06 | ~20s · skippable · <1.5 MB.
E-03 | 11 | Aliya | Epic E — Cutscenes & Anim | Lottie: puppet idles, celebration, tile flip | 8 |  | P1 | 24/06 | 26/06 | 5 files · <100 KB each · loop-safe.
F-07 | 12 | Aliya | Epic F — Art Assets | Backgrounds: World Intro + Backstory scenes | 6 |  | P2 | 23/06 | 24/06 | Consistent with style bible.
F-08 | 13 | Aliya | Epic F — Art Assets | Asset export optimization (WebP/AVIF/SVG) | 4 |  | P2 | 27/06 | 27/06 | Object <25 KB · BG <80 KB · tile <5 KB.
G-03 | 14 | Aliya | Epic G — Polish & QA | Pedagogy QA: narration audit vs ALfA | 4 |  | P1 | 30/06 | 01/07 | Flag any 'ब से बतख' violations.
G-08 | 15 | Aliya | Epic G — Polish & QA | Final asset QA + missing delivery | 6 |  | P1 | 01/07 | 02/07 | Audit all content JSON asset refs.
G-12 | 16 | Aliya | Epic G — Polish & QA | Demo prep: flow script + talking points | 3 |  | P2 | 03/07 | 04/07 | 10-min demo script for stakeholders.
Aliya Subtotal