## 📋 Overview
CAR + R Platform — 4-Sprint Development Plan
2 people (Naazish + Ishika) · 6 hrs/day · 6 days/week · 72 hrs/week · Release 1: 1 June · Final Release: End of Week 4
Sprint | Dates | Goal | Naazish (hrs) | Ishika (hrs) | Total (hrs) | Budget | Buffer | Release
Sprint 1 | Week 1 | Foundation & Infrastructure — Repo live, auth working, CI green | 34 | 16 | 50 | 72 | 22
Sprint 2 | Week 2 | Core Features — CARR loop functional, first internal release 1 June | 25.5 | 27.5 | 53 | 72 | 19 | 🚀 Release 1 — 1 June
Sprint 3 | Week 3 | Polish, Analyse & Coach tools — close feedback loop, Hindi support | 27.5 | 27.5 | 55 | 72 | 17
Sprint 4 | Week 4 | Research module, QA hardening, accessibility, final release | 30.5 | 25.5 | 56 | 72 | 16 | 🏁 Final Release
TOTALS |  |  | 117.5 | 96.5 | 214 | 288 | 74
Naazish
Ishika
Shared
P0 = Must-ship
P1 = Should-ship
P2 = Nice-to-have

## 🏗 Sprint 1 — Foundation
Sprint 1 — Foundation & Infrastructure — Repo live, auth working, CI green
Week 1 · Days 1–6 · ~72 hrs total · Budget: 72 hrs · Naazish: 36 hrs target · Ishika: 36 hrs target
ID | Task / Story | Epic | Owner | Hrs (N) | Hrs (I) | Total Hrs | Priority | Notes | D1 | D2 | D3 | D4 | D5 | D6 | Done?
0.7 | Define MVP scope & cut list | Foundation | Shared | 2 | 2 | 4 | P0 | Kickoff workshop — what ships, what doesn't | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
0.2 | Coach vs Admin role decision | Foundation | Shared | 1 | 1 | 2 | P0 | 2-hr decision session, document outcomes | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | ☐
0.1 | Tech stack & architecture decision | Foundation | Naazish | 8 | — | 8 | P0 | Repo, cloud env, DB schema, hosting provider | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | ☐
13.5 | CI/CD pipeline setup | Infra | Naazish | 6 | — | 6 | P0 | Deploy from Day 1 — velocity multiplier | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | ☐
1.1 | Teacher login — email / OTP | Auth | Ishika | — | 6 | 6 | P0 | JWT, session management, OTP via SMS | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | ☐
1.3 | Role-based access control (RBAC) | Auth | Naazish | 5 | — | 5 | P0 | Teacher / Coach / Admin roles | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
2.1 | Content data model | Content | Naazish | 4 | — | 4 | P1 | DB schema for modules & videos | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
2.3 | Video hosting & streaming — CDN | Content | Naazish | 8 | — | 8 | P0 | CDN integration — core platform bet | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | ☐
2.4 | Teacher content browse UI | Content | Ishika | — | 7 | 7 | P0 | List, filter, play modules on mobile | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | ☐
SPRINT TOTALS — Budget: 72 hrs ¦ Used: 50 hrs ¦ Buffer: 22 hrs |  |  | 34 | 16 | 50

## ⚡ Sprint 2 — Core
Sprint 2 — Core Features — CARR loop functional, first internal release 1 June
Week 2 · Days 7–12 · ~72 hrs total · Budget: 72 hrs · Naazish: 36 hrs target · Ishika: 36 hrs target
🚀 RELEASE 1 — 1 June (Internal / Pilot)
ID | Task / Story | Epic | Owner | Hrs (N) | Hrs (I) | Total Hrs | Priority | Notes | D1 | D2 | D3 | D4 | D5 | D6 | Done?
14.1 | DPDP consent flows | Compliance | Shared | 2.5 | 2.5 | 5 | P0 | Legal blocker — cannot launch without | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
14.2 | Privacy policy & T&C pages (documentation) | Compliance | Naazish | 2 | — | 2 | P1 | Static pages — cheap legal requirement | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | ☐
13.2 | Error tracking — Sentry | Infra | Suryansh | 2 | — | 2 | P1 | Production visibility from Day 1 | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | ☐
11.1 | Teacher information architecture | Teacher UX | Ishika | — | 5 | 5 | P0 | Nav, layout — defines daily experience | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
11.4 | Mobile-first responsive design | Teacher UX | Ishika | — | 7 | 7 | P0 | Teachers on mobile — non-negotiable | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | ☐
3.3 | Teacher test-taking UI — B0 / B1 | Assessment | Ishika | — | 5 | 5 | P0 | Pre & post test flow — B0 baseline | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
3.4 | Auto-scoring & result display | Assessment | Naazish | 4 | — | 4 | P0 | Score + correct-answer feedback | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
4.3 | Video metadata capture | Video | Ishika | — | 3 | 3 | P1 | Subject, grade, date, teacher tag | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
4.2 | Computer based video/photo upload — chunked | Video | Naazish | 10 | — | 10 | P0 | Chunked upload, progress bar, retry | 1.7h | 1.7h | 1.7h | 1.7h | 1.7h | 1.7h | ☐
4.4 | Video storage & lifecycle | Video | Naazish | 3 | — | 3 | P1 | Retention policy, cost guardrails | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
6.2 | Teacher reflection submission | Reflect | Ishika | — | 3 | 3 | P0 | Simple form — completes CARR loop | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
15.4 | UAT Session 1 — internal pilot | QA | Shared | 2 | 2 | 4 | P0 | 1 session × 4 teachers before Release 1 | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
SPRINT TOTALS — Budget: 72 hrs ¦ Used: 53.0 hrs ¦ Buffer: 19.0 hrs |  |  | 25.5 | 27.5 | 53

## 🔧 Sprint 3 — Polish
Sprint 3 — Polish, Analyse & Coach tools — close feedback loop, Hindi support
Week 3 · Days 13–18 · ~72 hrs total · Budget: 72 hrs · Naazish: 36 hrs target · Ishika: 36 hrs target
ID | Task / Story | Epic | Owner | Hrs (N) | Hrs (I) | Total Hrs | Priority | Notes | D1 | D2 | D3 | D4 | D5 | D6 | Done?
4.5 | Peer video review UI | Video | Shared | 2.5 | 2.5 | 5 | P0 | Timestamps + text notes on video | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐ | s2
4.6 | Teacher view of peer evaluation | Video | Ishika | — | 4 | 4 | P0 | Closes the Analyse loop for teacher | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐ | s2
11.2 | Hindi UI language support | Teacher UX | Ishika | — | 7 | 7 | P0 | Without Hindi product is unusable in UP | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | 1.2h | ☐ | s2
13.3 | Security hardening | Infra | Naazish | 4 | — | 4 | P0 | our content can not be shared to anyone | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
10.4 | Database backup & DR | Data | Naazish | 3 | — | 3 | P0 | Nightly backup + restore test | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
1.4 | Onboarding flow | Auth | Ishika | — | 3 | 3 | P1 | Was deferred from MVP — ship now | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
2.2 | Admin content CMS — basic | Content | Naazish | 8 | — | 8 | P1 | Coach can add/edit modules without DB | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | ☐
3.2 | Test composition UI — admin | Assessment | Naazish | 3 | — | 3 | P1 | Coach builds B0/B1 tests in UI | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐ | s2
8.1 | Dashboard KPI cards — principal | Dashboard | Shared | 2 | 3 | 5 | P1 | Registrations, completions, avg scores | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
1.5 | User management — admin | Auth | Naazish | 5 | — | 5 | P1 | Coach provisions teachers in UI | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
15.3 | Manual QA test plans | QA | Ishika | — | 4 | 4 | P1 | Happy-path + edge-case scripts | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
SPRINT TOTALS — Budget: 72 hrs ¦ Used: 55.0 hrs ¦ Buffer: 17.0 hrs |  |  | 27.5 | 27.5 | 55

## 🚀 Sprint 4 — Launch
Sprint 4 — Research module, QA hardening, accessibility, final release
Week 4 · Days 19–24 · ~72 hrs total · Budget: 72 hrs · Naazish: 36 hrs target · Ishika: 36 hrs target
🏁 FINAL RELEASE — End of Week 4 (Production)
ID | Task / Story | Epic | Owner | Hrs (N) | Hrs (I) | Total Hrs | Priority | Notes | D1 | D2 | D3 | D4 | D5 | D6 | Done?
7.1 | Research module — topic cards | Research | Ishika | — | 5 | 5 | P1 | + R section — teacher picks topic | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
7.2 | Research submission form & upload | Research | Ishika | — | 6 | 6 | P1 | Form, doc upload, confidence stars | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | 1.0h | ☐
7.3 | Research admin view | Research | Naazish | 4 | — | 4 | P1 | Coach sees all submissions + docs | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
5.1 | AI evaluation SPIKE | AI Engine | Naazish | 8 | — | 8 | P1 | Decide architecture — do not rush | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | 1.3h | ☐
11.3 | Accessibility audit & fixes | Teacher UX | Ishika | — | 5 | 5 | P1 | WCAG 2.1 AA pass — quality bar | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
9.1 | In-app notifications | Notifs | Naazish | 3 | — | 3 | P2 | Complements WhatsApp/SMS channel | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
13.4 | Load testing | Infra | Naazish | 3 | — | 3 | P1 | Simulate 50 concurrent teachers | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
15.1 | Unit test coverage — critical paths | QA | Naazish | 3 | — | 3 | P1 | Auth, assessment, video upload | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
15.2 | End-to-end test suite — Playwright | QA | Ishika | — | 5 | 5 | P1 | Full CARR loop automated | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
14.3 | Data subject rights page | Compliance | Naazish | 5 | — | 5 | P1 | DPDP full compliance | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | 0.8h | ☐
15.4 | UAT Session 2 — external teachers | QA | Shared | 2 | 2 | 4 | P0 | 2 sessions × 5 teachers | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | 0.7h | ☐
16.1 | Pilot cohort selection & briefing | Launch | Shared | 1 | 1 | 2 | P0 | Pick 10–15 teachers for production | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | 0.3h | ☐
16.2 | Production launch runbook | Launch | Shared | 1.5 | 1.5 | 3 | P0 | Ops checklist, rollback plan, comms | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | 0.5h | ☐
SPRINT TOTALS — Budget: 72 hrs ¦ Used: 56.0 hrs ¦ Buffer: 16.0 hrs |  |  | 30.5 | 25.5 | 56

## 📊 Master Task List
CAR + R — Master Task List · All Sprints · All Owners
Sprint | ID | Task / Story | Epic | Owner | Hrs (N) | Hrs (I) | Total | Priority | Notes | Status
Sprint 1 | 0.7 | Define MVP scope & cut list | Foundation | Shared | 2 | 2 | 4 | P0 | Kickoff workshop — what ships, what doesn't | ☐ Not started
Sprint 1 | 0.2 | Coach vs Admin role decision | Foundation | Shared | 1 | 1 | 2 | P0 | 2-hr decision session, document outcomes | ☐ Not started
Sprint 1 | 0.1 | Tech stack & architecture decision | Foundation | Naazish | 8 | — | 8 | P0 | Repo, cloud env, DB schema, hosting provider | ☐ Not started
Sprint 1 | 13.5 | CI/CD pipeline setup | Infra | Naazish | 6 | — | 6 | P0 | Deploy from Day 1 — velocity multiplier | ☐ Not started
Sprint 1 | 1.1 | Teacher login — email / OTP | Auth | Ishika | — | 6 | 6 | P0 | JWT, session management, OTP via SMS | ☐ Not started
Sprint 1 | 1.3 | Role-based access control (RBAC) | Auth | Naazish | 5 | — | 5 | P0 | Teacher / Coach / Admin roles | ☐ Not started
Sprint 1 | 2.1 | Content data model | Content | Naazish | 4 | — | 4 | P1 | DB schema for modules & videos | ☐ Not started
Sprint 1 | 2.3 | Video hosting & streaming — CDN | Content | Naazish | 8 | — | 8 | P0 | CDN integration — core platform bet | ☐ Not started
Sprint 1 | 2.4 | Teacher content browse UI | Content | Ishika | — | 7 | 7 | P0 | List, filter, play modules on mobile | ☐ Not started
Sprint 2 | 14.1 | DPDP consent flows | Compliance | Shared | 2.5 | 2.5 | 5 | P0 | Legal blocker — cannot launch without | ☐ Not started
Sprint 2 | 14.2 | Privacy policy & T&C pages | Compliance | Naazish | 2 | — | 2 | P1 | Static pages — cheap legal requirement | ☐ Not started
Sprint 2 | 13.2 | Error tracking — Sentry | Infra | Naazish | 2 | — | 2 | P1 | Production visibility from Day 1 | ☐ Not started
Sprint 2 | 11.1 | Teacher information architecture | Teacher UX | Ishika | — | 5 | 5 | P0 | Nav, layout — defines daily experience | ☐ Not started
Sprint 2 | 11.4 | Mobile-first responsive design | Teacher UX | Ishika | — | 7 | 7 | P0 | Teachers on mobile — non-negotiable | ☐ Not started
Sprint 2 | 3.3 | Teacher test-taking UI — B0 / B1 | Assessment | Ishika | — | 5 | 5 | P0 | Pre & post test flow — B0 baseline | ☐ Not started
Sprint 2 | 3.4 | Auto-scoring & result display | Assessment | Naazish | 4 | — | 4 | P0 | Score + correct-answer feedback | ☐ Not started
Sprint 2 | 4.3 | Video metadata capture | Video | Ishika | — | 3 | 3 | P1 | Subject, grade, date, teacher tag | ☐ Not started
Sprint 2 | 4.2 | Mobile video upload — chunked | Video | Naazish | 10 | — | 10 | P0 | Chunked upload, progress bar, retry | ☐ Not started
Sprint 2 | 4.4 | Video storage & lifecycle | Video | Naazish | 3 | — | 3 | P1 | Retention policy, cost guardrails | ☐ Not started
Sprint 2 | 6.2 | Teacher reflection submission | Reflect | Ishika | — | 3 | 3 | P0 | Simple form — completes CARR loop | ☐ Not started
Sprint 2 | 15.4 | UAT Session 1 — internal pilot | QA | Shared | 2 | 2 | 4 | P0 | 1 session × 4 teachers before Release 1 | ☐ Not started
Sprint 3 | 4.5 | Coach video review UI | Video | Shared | 2.5 | 2.5 | 5 | P0 | Timestamps + text notes on video | ☐ Not started
Sprint 3 | 4.6 | Teacher view of coach feedback | Video | Ishika | — | 4 | 4 | P0 | Closes the Analyse loop for teacher | ☐ Not started
Sprint 3 | 11.2 | Hindi UI language support | Teacher UX | Ishika | — | 7 | 7 | P0 | Without Hindi product is unusable in UP | ☐ Not started
Sprint 3 | 9.3 | WhatsApp / SMS notifications | Notifs | Ishika | — | 4 | 4 | P0 | Most reliable channel for UP teachers | ☐ Not started
Sprint 3 | 13.3 | Security hardening | Infra | Naazish | 4 | — | 4 | P0 | OWASP top-10, auth hardening | ☐ Not started
Sprint 3 | 10.4 | Database backup & DR | Data | Naazish | 3 | — | 3 | P0 | Nightly backup + restore test | ☐ Not started
Sprint 3 | 1.4 | Onboarding flow | Auth | Ishika | — | 3 | 3 | P1 | Was deferred from MVP — ship now | ☐ Not started
Sprint 3 | 2.2 | Admin content CMS — basic | Content | Naazish | 8 | — | 8 | P1 | Coach can add/edit modules without DB | ☐ Not started
Sprint 3 | 3.2 | Test composition UI — admin | Assessment | Naazish | 3 | — | 3 | P1 | Coach builds B0/B1 tests in UI | ☐ Not started
Sprint 3 | 8.1 | Dashboard KPI cards — coach | Dashboard | Shared | 2 | 3 | 5 | P1 | Registrations, completions, avg scores | ☐ Not started
Sprint 3 | 1.5 | User management — admin | Auth | Naazish | 5 | — | 5 | P1 | Coach provisions teachers in UI | ☐ Not started
Sprint 3 | 15.3 | Manual QA test plans | QA | Ishika | — | 4 | 4 | P1 | Happy-path + edge-case scripts | ☐ Not started
Sprint 4 | 7.1 | Research module — topic cards | Research | Ishika | — | 5 | 5 | P1 | + R section — teacher picks topic | ☐ Not started
Sprint 4 | 7.2 | Research submission form & upload | Research | Ishika | — | 6 | 6 | P1 | Form, doc upload, confidence stars | ☐ Not started
Sprint 4 | 7.3 | Research admin view | Research | Naazish | 4 | — | 4 | P1 | Coach sees all submissions + docs | ☐ Not started
Sprint 4 | 5.1 | AI evaluation SPIKE | AI Engine | Naazish | 8 | — | 8 | P1 | Decide architecture — do not rush | ☐ Not started
Sprint 4 | 11.3 | Accessibility audit & fixes | Teacher UX | Ishika | — | 5 | 5 | P1 | WCAG 2.1 AA pass — quality bar | ☐ Not started
Sprint 4 | 9.1 | In-app notifications | Notifs | Naazish | 3 | — | 3 | P2 | Complements WhatsApp/SMS channel | ☐ Not started
Sprint 4 | 13.4 | Load testing | Infra | Naazish | 3 | — | 3 | P1 | Simulate 50 concurrent teachers | ☐ Not started
Sprint 4 | 15.1 | Unit test coverage — critical paths | QA | Naazish | 3 | — | 3 | P1 | Auth, assessment, video upload | ☐ Not started
Sprint 4 | 15.2 | End-to-end test suite — Playwright | QA | Ishika | — | 5 | 5 | P1 | Full CARR loop automated | ☐ Not started
Sprint 4 | 14.3 | Data subject rights page | Compliance | Naazish | 5 | — | 5 | P1 | DPDP full compliance | ☐ Not started
Sprint 4 | 15.4 | UAT Session 2 — external teachers | QA | Shared | 2 | 2 | 4 | P0 | 2 sessions × 5 teachers | ☐ Not started
Sprint 4 | 16.1 | Pilot cohort selection & briefing | Launch | Shared | 1 | 1 | 2 | P0 | Pick 10–15 teachers for production | ☐ Not started
Sprint 4 | 16.2 | Production launch runbook | Launch | Shared | 1.5 | 1.5 | 3 | P0 | Ops checklist, rollback plan, comms | ☐ Not started

## 👤 Naazish Board
Naazish — Personal Sprint Board · 36 hrs/week target
Sprint | ID | Task / Story | Epic | My Hrs | Priority | Notes | Day Target | Done?
Sprint 1 | 0.7 | Define MVP scope & cut list | Foundation | 2 | P0 | Kickoff workshop — what ships, what doesn't | ~0.3 hrs/day | ☐
Sprint 1 | 0.2 | Coach vs Admin role decision | Foundation | 1 | P0 | 2-hr decision session, document outcomes | ~0.2 hrs/day | ☐
Sprint 1 | 0.1 | Tech stack & architecture decision | Foundation | 8 | P0 | Repo, cloud env, DB schema, hosting provider | ~1.3 hrs/day | ☐
Sprint 1 | 13.5 | CI/CD pipeline setup | Infra | 6 | P0 | Deploy from Day 1 — velocity multiplier | ~1.0 hrs/day | ☐
Sprint 1 | 1.3 | Role-based access control (RBAC) | Auth | 5 | P0 | Teacher / Coach / Admin roles | ~0.8 hrs/day | ☐
Sprint 1 | 2.1 | Content data model | Content | 4 | P1 | DB schema for modules & videos | ~0.7 hrs/day | ☐
Sprint 1 | 2.3 | Video hosting & streaming — CDN | Content | 8 | P0 | CDN integration — core platform bet | ~1.3 hrs/day | ☐
Sprint 2 | 14.1 | DPDP consent flows | Compliance | 2.5 | P0 | Legal blocker — cannot launch without | ~0.4 hrs/day | ☐
Sprint 2 | 14.2 | Privacy policy & T&C pages | Compliance | 2 | P1 | Static pages — cheap legal requirement | ~0.3 hrs/day | ☐
Sprint 2 | 13.2 | Error tracking — Sentry | Infra | 2 | P1 | Production visibility from Day 1 | ~0.3 hrs/day | ☐
Sprint 2 | 3.4 | Auto-scoring & result display | Assessment | 4 | P0 | Score + correct-answer feedback | ~0.7 hrs/day | ☐
Sprint 2 | 4.2 | Mobile video upload — chunked | Video | 10 | P0 | Chunked upload, progress bar, retry | ~1.7 hrs/day | ☐
Sprint 2 | 4.4 | Video storage & lifecycle | Video | 3 | P1 | Retention policy, cost guardrails | ~0.5 hrs/day | ☐
Sprint 2 | 15.4 | UAT Session 1 — internal pilot | QA | 2 | P0 | 1 session × 4 teachers before Release 1 | ~0.3 hrs/day | ☐
Sprint 3 | 4.5 | Coach video review UI | Video | 2.5 | P0 | Timestamps + text notes on video | ~0.4 hrs/day | ☐
Sprint 3 | 13.3 | Security hardening | Infra | 4 | P0 | OWASP top-10, auth hardening | ~0.7 hrs/day | ☐
Sprint 3 | 10.4 | Database backup & DR | Data | 3 | P0 | Nightly backup + restore test | ~0.5 hrs/day | ☐
Sprint 3 | 2.2 | Admin content CMS — basic | Content | 8 | P1 | Coach can add/edit modules without DB | ~1.3 hrs/day | ☐
Sprint 3 | 3.2 | Test composition UI — admin | Assessment | 3 | P1 | Coach builds B0/B1 tests in UI | ~0.5 hrs/day | ☐
Sprint 3 | 8.1 | Dashboard KPI cards — coach | Dashboard | 2 | P1 | Registrations, completions, avg scores | ~0.3 hrs/day | ☐
Sprint 3 | 1.5 | User management — admin | Auth | 5 | P1 | Coach provisions teachers in UI | ~0.8 hrs/day | ☐
Sprint 4 | 7.3 | Research admin view | Research | 4 | P1 | Coach sees all submissions + docs | ~0.7 hrs/day | ☐
Sprint 4 | 5.1 | AI evaluation SPIKE | AI Engine | 8 | P1 | Decide architecture — do not rush | ~1.3 hrs/day | ☐
Sprint 4 | 9.1 | In-app notifications | Notifs | 3 | P2 | Complements WhatsApp/SMS channel | ~0.5 hrs/day | ☐
Sprint 4 | 13.4 | Load testing | Infra | 3 | P1 | Simulate 50 concurrent teachers | ~0.5 hrs/day | ☐
Sprint 4 | 15.1 | Unit test coverage — critical paths | QA | 3 | P1 | Auth, assessment, video upload | ~0.5 hrs/day | ☐
Sprint 4 | 14.3 | Data subject rights page | Compliance | 5 | P1 | DPDP full compliance | ~0.8 hrs/day | ☐
Sprint 4 | 15.4 | UAT Session 2 — external teachers | QA | 2 | P0 | 2 sessions × 5 teachers | ~0.3 hrs/day | ☐
Sprint 4 | 16.1 | Pilot cohort selection & briefing | Launch | 1 | P0 | Pick 10–15 teachers for production | ~0.2 hrs/day | ☐
Sprint 4 | 16.2 | Production launch runbook | Launch | 1.5 | P0 | Ops checklist, rollback plan, comms | ~0.2 hrs/day | ☐

## 👤 Ishika Board
Ishika — Personal Sprint Board · 36 hrs/week target
Sprint | ID | Task / Story | Epic | My Hrs | Priority | Notes | Day Target | Done?
Sprint 1 | 0.7 | Define MVP scope & cut list | Foundation | 2 | P0 | Kickoff workshop — what ships, what doesn't | ~0.3 hrs/day | ☐
Sprint 1 | 0.2 | Coach vs Admin role decision | Foundation | 1 | P0 | 2-hr decision session, document outcomes | ~0.2 hrs/day | ☐
Sprint 1 | 1.1 | Teacher login — email / OTP | Auth | 6 | P0 | JWT, session management, OTP via SMS | ~1.0 hrs/day | ☐
Sprint 1 | 2.4 | Teacher content browse UI | Content | 7 | P0 | List, filter, play modules on mobile | ~1.2 hrs/day | ☐
Sprint 2 | 14.1 | DPDP consent flows | Compliance | 2.5 | P0 | Legal blocker — cannot launch without | ~0.4 hrs/day | ☐
Sprint 2 | 11.1 | Teacher information architecture | Teacher UX | 5 | P0 | Nav, layout — defines daily experience | ~0.8 hrs/day | ☐
Sprint 2 | 11.4 | Mobile-first responsive design | Teacher UX | 7 | P0 | Teachers on mobile — non-negotiable | ~1.2 hrs/day | ☐
Sprint 2 | 3.3 | Teacher test-taking UI — B0 / B1 | Assessment | 5 | P0 | Pre & post test flow — B0 baseline | ~0.8 hrs/day | ☐
Sprint 2 | 4.3 | Video metadata capture | Video | 3 | P1 | Subject, grade, date, teacher tag | ~0.5 hrs/day | ☐
Sprint 2 | 6.2 | Teacher reflection submission | Reflect | 3 | P0 | Simple form — completes CARR loop | ~0.5 hrs/day | ☐
Sprint 2 | 15.4 | UAT Session 1 — internal pilot | QA | 2 | P0 | 1 session × 4 teachers before Release 1 | ~0.3 hrs/day | ☐
Sprint 3 | 4.5 | Coach video review UI | Video | 2.5 | P0 | Timestamps + text notes on video | ~0.4 hrs/day | ☐
Sprint 3 | 4.6 | Teacher view of coach feedback | Video | 4 | P0 | Closes the Analyse loop for teacher | ~0.7 hrs/day | ☐
Sprint 3 | 11.2 | Hindi UI language support | Teacher UX | 7 | P0 | Without Hindi product is unusable in UP | ~1.2 hrs/day | ☐
Sprint 3 | 9.3 | WhatsApp / SMS notifications | Notifs | 4 | P0 | Most reliable channel for UP teachers | ~0.7 hrs/day | ☐
Sprint 3 | 1.4 | Onboarding flow | Auth | 3 | P1 | Was deferred from MVP — ship now | ~0.5 hrs/day | ☐
Sprint 3 | 8.1 | Dashboard KPI cards — coach | Dashboard | 3 | P1 | Registrations, completions, avg scores | ~0.5 hrs/day | ☐
Sprint 3 | 15.3 | Manual QA test plans | QA | 4 | P1 | Happy-path + edge-case scripts | ~0.7 hrs/day | ☐
Sprint 4 | 7.1 | Research module — topic cards | Research | 5 | P1 | + R section — teacher picks topic | ~0.8 hrs/day | ☐
Sprint 4 | 7.2 | Research submission form & upload | Research | 6 | P1 | Form, doc upload, confidence stars | ~1.0 hrs/day | ☐
Sprint 4 | 11.3 | Accessibility audit & fixes | Teacher UX | 5 | P1 | WCAG 2.1 AA pass — quality bar | ~0.8 hrs/day | ☐
Sprint 4 | 15.2 | End-to-end test suite — Playwright | QA | 5 | P1 | Full CARR loop automated | ~0.8 hrs/day | ☐
Sprint 4 | 15.4 | UAT Session 2 — external teachers | QA | 2 | P0 | 2 sessions × 5 teachers | ~0.3 hrs/day | ☐
Sprint 4 | 16.1 | Pilot cohort selection & briefing | Launch | 1 | P0 | Pick 10–15 teachers for production | ~0.2 hrs/day | ☐
Sprint 4 | 16.2 | Production launch runbook | Launch | 1.5 | P0 | Ops checklist, rollback plan, comms | ~0.2 hrs/day | ☐

## 🔕 Deferred Backlog
Deferred Backlog — Schedule post Week 4 per 18-week plan
ID | Story | Epic | Est Hrs | Why Deferred / When to Revisit
5.1 | AI evaluation SPIKE | AI Engine | 8 | Needs a dedicated sprint — wrong architecture risks production failure
5.2 | Audio transcription | AI Engine | 5 | Post-SPIKE only — deploy after AI path is decided
5.3 | Talk-time metrics | AI Engine | 8 | Same — AI engine must be scoped first
3.5 | Test integrity checks | Assessment | 3 | Quality of data, not user-facing — defer to Week 5
3.6 | Student data ingestion | Assessment | 8 | Adoption risk too high for MVP; manual entry if needed
9.1 | In-app notifications | Notifs | 3 | WhatsApp/SMS covers pilot reliably (moved to Sprint 4)
11.5 | Onboarding tutorial | Teacher UX | 3 | Replaced by live guidance during UAT sessions
13.4 | Load testing | Infra | 3 | Pilot 10–15 teachers; load test before scaling (Week 6)
15.1 | Unit test coverage | QA | 3 | Manual QA covers MVP; unit tests Sprint 3+
15.2 | E2E test suite | QA | 5 | Automated E2E post-MVP; manual plan ships instead